## Gantt
ID | Name | Start | Finish | Duration | % Complete | Predecessors | Resource Names | Approval Required | Materials | Owner | Target Start | Target Finish | Remarks | Outline Level | Color
1 | Project Kickoff | 2024-01-01 | 2024-01-01 | 1 | 100 |  | Project Manager | N |  | PM Team | 2024-01-01 | 2024-01-01 | Initial project kickoff meeting | 1
2 | Design Phase | 2024-01-02 | 2024-01-08 | 7 | 75 | 1FS+0 | Designer, Architect | Y | Design Software | Design Team | 2024-01-02 | 2024-01-08 | Complete schematic designs | 2 | #4A90E2
3 | Client Approval | 2024-01-09 | 2024-01-11 | 3 | 50 | 2FS+0 | Client Coordinator | Y |  | Client Relations | 2024-01-09 | 2024-01-11 | Awaiting client sign-off | 2 | #F5A623
4 | Construction | 2024-01-12 | 2024-01-26 | 15 | 20 | 3FS+0 | Construction Team | N | Wood, Paint, Fixtures | Construction Lead | 2024-01-12 | 2024-01-26 | Main construction phase | 1 | #7ED321
5 | Final Inspection | 2024-01-26 | 2024-01-27 | 2 | 0 | 4SS+0 | Inspector | Y |  | Quality Team | 2024-01-26 | 2024-01-27 | Final quality check - using Start-to-Start dependency | 2