## Gantt
ID | Name | Start | Finish | Duration | % Complete | Predecessors | Resource Names | Approval Required | Materials | Owner | Target Start | Target Finish | Remarks | Outline Level | Color
1 | PHASE • Design & Approvals |  |  |  | 0 |  |  | N | [5 empty] | 1
2 | Client Brief & Scope |  |  | 2 | 0 |  | Designer | N | [5 empty] | 2
3 | Schematic Drawings (Overall) |  |  | 5 | 0 | 2FS+0 | Designer | N | [5 empty] | 2
4 | Working Drawings (Overall) |  |  | 7 | 0 | 3FS+0 | Designer | N | [5 empty] | 2
5 | Finishes Board & Samples (Overall) |  |  | 3 | 0 | 3FS+0 | Designer | Y | [5 empty] | 2
6 | Client Sign‑off (Drawings & Finishes) |  |  | 1 | 0 | 4FS+0,5FS+0 | Client | Y |  |  |  | Milestone |  | 2
7 | PHASE • Vendor Evaluation → Quotes → Finalisation → Work Orders |  |  |  | 0 |  |  | N | [5 empty] | 1
8 | PACKAGE • Civil |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
9 | Civil: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 8FS+0 | Designer | N | [5 empty] | 2
10 | Civil: Vendor Meetings / Site Survey |  |  | 2 | 0 | 9FS+0 | Designer+Vendor | N | [5 empty] | 2
11 | Civil: RFQs Issued |  |  | 2 | 0 | 10FS+0 | Designer | N | [5 empty] | 2
12 | Civil: Quotes Received & Clarifications |  |  | 3 | 0 | 11FS+0 | Designer | N | [5 empty] | 2
13 | Civil: Quote Comparison & Negotiation |  |  | 2 | 0 | 12FS+0 | Designer | N | [5 empty] | 2
14 | Civil: Vendor Finalisation |  |  | 1 | 0 | 13FS+0 | Designer+Client | Y | [5 empty] | 2
15 | Civil: Work Order / PO Release |  |  | 1 | 0 | 14FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
16 | PACKAGE • Electricals |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
17 | Electricals: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 16FS+0 | Designer | N | [5 empty] | 2
18 | Electricals: Vendor Meetings / Site Survey |  |  | 2 | 0 | 17FS+0 | Designer+Vendor | N | [5 empty] | 2
19 | Electricals: RFQs Issued |  |  | 2 | 0 | 18FS+0 | Designer | N | [5 empty] | 2
20 | Electricals: Quotes Received & Clarifications |  |  | 3 | 0 | 19FS+0 | Designer | N | [5 empty] | 2
21 | Electricals: Quote Comparison & Negotiation |  |  | 2 | 0 | 20FS+0 | Designer | N | [5 empty] | 2
22 | Electricals: Vendor Finalisation |  |  | 1 | 0 | 21FS+0 | Designer+Client | Y | [5 empty] | 2
23 | Electricals: Work Order / PO Release |  |  | 1 | 0 | 22FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
24 | PACKAGE • Plumbing |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
25 | Plumbing: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 24FS+0 | Designer | N | [5 empty] | 2
26 | Plumbing: Vendor Meetings / Site Survey |  |  | 2 | 0 | 25FS+0 | Designer+Vendor | N | [5 empty] | 2
27 | Plumbing: RFQs Issued |  |  | 2 | 0 | 26FS+0 | Designer | N | [5 empty] | 2
28 | Plumbing: Quotes Received & Clarifications |  |  | 3 | 0 | 27FS+0 | Designer | N | [5 empty] | 2
29 | Plumbing: Quote Comparison & Negotiation |  |  | 2 | 0 | 28FS+0 | Designer | N | [5 empty] | 2
30 | Plumbing: Vendor Finalisation |  |  | 1 | 0 | 29FS+0 | Designer+Client | Y | [5 empty] | 2
31 | Plumbing: Work Order / PO Release |  |  | 1 | 0 | 30FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
32 | PACKAGE • Kitchens |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
33 | Kitchens: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 32FS+0 | Designer | N | [5 empty] | 2
34 | Kitchens: Vendor Meetings / Site Survey |  |  | 2 | 0 | 33FS+0 | Designer+Vendor | N | [5 empty] | 2
35 | Kitchens: RFQs Issued |  |  | 2 | 0 | 34FS+0 | Designer | N | [5 empty] | 2
36 | Kitchens: Quotes Received & Clarifications |  |  | 3 | 0 | 35FS+0 | Designer | N | [5 empty] | 2
37 | Kitchens: Quote Comparison & Negotiation |  |  | 2 | 0 | 36FS+0 | Designer | N | [5 empty] | 2
38 | Kitchens: Vendor Finalisation |  |  | 1 | 0 | 37FS+0 | Designer+Client | Y | [5 empty] | 2
39 | Kitchens: Work Order / PO Release |  |  | 1 | 0 | 38FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
40 | PACKAGE • Bathrooms |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
41 | Bathrooms: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 40FS+0 | Designer | N | [5 empty] | 2
42 | Bathrooms: Vendor Meetings / Site Survey |  |  | 2 | 0 | 41FS+0 | Designer+Vendor | N | [5 empty] | 2
43 | Bathrooms: RFQs Issued |  |  | 2 | 0 | 42FS+0 | Designer | N | [5 empty] | 2
44 | Bathrooms: Quotes Received & Clarifications |  |  | 3 | 0 | 43FS+0 | Designer | N | [5 empty] | 2
45 | Bathrooms: Quote Comparison & Negotiation |  |  | 2 | 0 | 44FS+0 | Designer | N | [5 empty] | 2
46 | Bathrooms: Vendor Finalisation |  |  | 1 | 0 | 45FS+0 | Designer+Client | Y | [5 empty] | 2
47 | Bathrooms: Work Order / PO Release |  |  | 1 | 0 | 46FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
48 | PACKAGE • Audio |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
49 | Audio: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 48FS+0 | Designer | N | [5 empty] | 2
50 | Audio: Vendor Meetings / Site Survey |  |  | 2 | 0 | 49FS+0 | Designer+Vendor | N | [5 empty] | 2
51 | Audio: RFQs Issued |  |  | 2 | 0 | 50FS+0 | Designer | N | [5 empty] | 2
52 | Audio: Quotes Received & Clarifications |  |  | 3 | 0 | 51FS+0 | Designer | N | [5 empty] | 2
53 | Audio: Quote Comparison & Negotiation |  |  | 2 | 0 | 52FS+0 | Designer | N | [5 empty] | 2
54 | Audio: Vendor Finalisation |  |  | 1 | 0 | 53FS+0 | Designer+Client | Y | [5 empty] | 2
55 | Audio: Work Order / PO Release |  |  | 1 | 0 | 54FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
56 | PACKAGE • Automation |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
57 | Automation: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 56FS+0 | Designer | N | [5 empty] | 2
58 | Automation: Vendor Meetings / Site Survey |  |  | 2 | 0 | 57FS+0 | Designer+Vendor | N | [5 empty] | 2
59 | Automation: RFQs Issued |  |  | 2 | 0 | 58FS+0 | Designer | N | [5 empty] | 2
60 | Automation: Quotes Received & Clarifications |  |  | 3 | 0 | 59FS+0 | Designer | N | [5 empty] | 2
61 | Automation: Quote Comparison & Negotiation |  |  | 2 | 0 | 60FS+0 | Designer | N | [5 empty] | 2
62 | Automation: Vendor Finalisation |  |  | 1 | 0 | 61FS+0 | Designer+Client | Y | [5 empty] | 2
63 | Automation: Work Order / PO Release |  |  | 1 | 0 | 62FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
64 | PACKAGE • Lighting |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
65 | Lighting: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 64FS+0 | Designer | N | [5 empty] | 2
66 | Lighting: Vendor Meetings / Site Survey |  |  | 2 | 0 | 65FS+0 | Designer+Vendor | N | [5 empty] | 2
67 | Lighting: RFQs Issued |  |  | 2 | 0 | 66FS+0 | Designer | N | [5 empty] | 2
68 | Lighting: Quotes Received & Clarifications |  |  | 3 | 0 | 67FS+0 | Designer | N | [5 empty] | 2
69 | Lighting: Quote Comparison & Negotiation |  |  | 2 | 0 | 68FS+0 | Designer | N | [5 empty] | 2
70 | Lighting: Vendor Finalisation |  |  | 1 | 0 | 69FS+0 | Designer+Client | Y | [5 empty] | 2
71 | Lighting: Work Order / PO Release |  |  | 1 | 0 | 70FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
72 | PACKAGE • HVAC |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
73 | HVAC: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 72FS+0 | Designer | N | [5 empty] | 2
74 | HVAC: Vendor Meetings / Site Survey |  |  | 2 | 0 | 73FS+0 | Designer+Vendor | N | [5 empty] | 2
75 | HVAC: RFQs Issued |  |  | 2 | 0 | 74FS+0 | Designer | N | [5 empty] | 2
76 | HVAC: Quotes Received & Clarifications |  |  | 3 | 0 | 75FS+0 | Designer | N | [5 empty] | 2
77 | HVAC: Quote Comparison & Negotiation |  |  | 2 | 0 | 76FS+0 | Designer | N | [5 empty] | 2
78 | HVAC: Vendor Finalisation |  |  | 1 | 0 | 77FS+0 | Designer+Client | Y | [5 empty] | 2
79 | HVAC: Work Order / PO Release |  |  | 1 | 0 | 78FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
80 | PACKAGE • Doors & Windows |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
81 | Doors & Windows: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 80FS+0 | Designer | N | [5 empty] | 2
82 | Doors & Windows: Vendor Meetings / Site Survey |  |  | 2 | 0 | 81FS+0 | Designer+Vendor | N | [5 empty] | 2
83 | Doors & Windows: RFQs Issued |  |  | 2 | 0 | 82FS+0 | Designer | N | [5 empty] | 2
84 | Doors & Windows: Quotes Received & Clarifications |  |  | 3 | 0 | 83FS+0 | Designer | N | [5 empty] | 2
85 | Doors & Windows: Quote Comparison & Negotiation |  |  | 2 | 0 | 84FS+0 | Designer | N | [5 empty] | 2
86 | Doors & Windows: Vendor Finalisation |  |  | 1 | 0 | 85FS+0 | Designer+Client | Y | [5 empty] | 2
87 | Doors & Windows: Work Order / PO Release |  |  | 1 | 0 | 86FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
88 | PACKAGE • Wall Finishes |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
89 | Wall Finishes: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 88FS+0 | Designer | N | [5 empty] | 2
90 | Wall Finishes: Vendor Meetings / Site Survey |  |  | 2 | 0 | 89FS+0 | Designer+Vendor | N | [5 empty] | 2
91 | Wall Finishes: RFQs Issued |  |  | 2 | 0 | 90FS+0 | Designer | N | [5 empty] | 2
92 | Wall Finishes: Quotes Received & Clarifications |  |  | 3 | 0 | 91FS+0 | Designer | N | [5 empty] | 2
93 | Wall Finishes: Quote Comparison & Negotiation |  |  | 2 | 0 | 92FS+0 | Designer | N | [5 empty] | 2
94 | Wall Finishes: Vendor Finalisation |  |  | 1 | 0 | 93FS+0 | Designer+Client | Y | [5 empty] | 2
95 | Wall Finishes: Work Order / PO Release |  |  | 1 | 0 | 94FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
96 | PACKAGE • Furnishing |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
97 | Furnishing: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 96FS+0 | Designer | N | [5 empty] | 2
98 | Furnishing: Vendor Meetings / Site Survey |  |  | 2 | 0 | 97FS+0 | Designer+Vendor | N | [5 empty] | 2
99 | Furnishing: RFQs Issued |  |  | 2 | 0 | 98FS+0 | Designer | N | [5 empty] | 2
100 | Furnishing: Quotes Received & Clarifications |  |  | 3 | 0 | 99FS+0 | Designer | N | [5 empty] | 2
101 | Furnishing: Quote Comparison & Negotiation |  |  | 2 | 0 | 100FS+0 | Designer | N | [5 empty] | 2
102 | Furnishing: Vendor Finalisation |  |  | 1 | 0 | 101FS+0 | Designer+Client | Y | [5 empty] | 2
103 | Furnishing: Work Order / PO Release |  |  | 1 | 0 | 102FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
104 | PACKAGE • Soft Furnishing |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
105 | Soft Furnishing: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 104FS+0 | Designer | N | [5 empty] | 2
106 | Soft Furnishing: Vendor Meetings / Site Survey |  |  | 2 | 0 | 105FS+0 | Designer+Vendor | N | [5 empty] | 2
107 | Soft Furnishing: RFQs Issued |  |  | 2 | 0 | 106FS+0 | Designer | N | [5 empty] | 2
108 | Soft Furnishing: Quotes Received & Clarifications |  |  | 3 | 0 | 107FS+0 | Designer | N | [5 empty] | 2
109 | Soft Furnishing: Quote Comparison & Negotiation |  |  | 2 | 0 | 108FS+0 | Designer | N | [5 empty] | 2
110 | Soft Furnishing: Vendor Finalisation |  |  | 1 | 0 | 109FS+0 | Designer+Client | Y | [5 empty] | 2
111 | Soft Furnishing: Work Order / PO Release |  |  | 1 | 0 | 110FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
112 | PACKAGE • Appliances |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
113 | Appliances: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 112FS+0 | Designer | N | [5 empty] | 2
114 | Appliances: Vendor Meetings / Site Survey |  |  | 2 | 0 | 113FS+0 | Designer+Vendor | N | [5 empty] | 2
115 | Appliances: RFQs Issued |  |  | 2 | 0 | 114FS+0 | Designer | N | [5 empty] | 2
116 | Appliances: Quotes Received & Clarifications |  |  | 3 | 0 | 115FS+0 | Designer | N | [5 empty] | 2
117 | Appliances: Quote Comparison & Negotiation |  |  | 2 | 0 | 116FS+0 | Designer | N | [5 empty] | 2
118 | Appliances: Vendor Finalisation |  |  | 1 | 0 | 117FS+0 | Designer+Client | Y | [5 empty] | 2
119 | Appliances: Work Order / PO Release |  |  | 1 | 0 | 118FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
120 | PACKAGE • Flooring |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
121 | Flooring: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 120FS+0 | Designer | N | [5 empty] | 2
122 | Flooring: Vendor Meetings / Site Survey |  |  | 2 | 0 | 121FS+0 | Designer+Vendor | N | [5 empty] | 2
123 | Flooring: RFQs Issued |  |  | 2 | 0 | 122FS+0 | Designer | N | [5 empty] | 2
124 | Flooring: Quotes Received & Clarifications |  |  | 3 | 0 | 123FS+0 | Designer | N | [5 empty] | 2
125 | Flooring: Quote Comparison & Negotiation |  |  | 2 | 0 | 124FS+0 | Designer | N | [5 empty] | 2
126 | Flooring: Vendor Finalisation |  |  | 1 | 0 | 125FS+0 | Designer+Client | Y | [5 empty] | 2
127 | Flooring: Work Order / PO Release |  |  | 1 | 0 | 126FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
128 | PACKAGE • Carpentry |  |  |  | 0 | 6FS+0 |  | N | [5 empty] | 1
129 | Carpentry: Vendor Evaluation (shortlist) |  |  | 3 | 0 | 128FS+0 | Designer | N | [5 empty] | 2
130 | Carpentry: Vendor Meetings / Site Survey |  |  | 2 | 0 | 129FS+0 | Designer+Vendor | N | [5 empty] | 2
131 | Carpentry: RFQs Issued |  |  | 2 | 0 | 130FS+0 | Designer | N | [5 empty] | 2
132 | Carpentry: Quotes Received & Clarifications |  |  | 3 | 0 | 131FS+0 | Designer | N | [5 empty] | 2
133 | Carpentry: Quote Comparison & Negotiation |  |  | 2 | 0 | 132FS+0 | Designer | N | [5 empty] | 2
134 | Carpentry: Vendor Finalisation |  |  | 1 | 0 | 133FS+0 | Designer+Client | Y | [5 empty] | 2
135 | Carpentry: Work Order / PO Release |  |  | 1 | 0 | 134FS+0 | Designer | Y |  |  |  | Gate for execution |  | 2
136 | PHASE • Execution (Category-wise) |  |  |  | 0 |  |  | N | [5 empty] | 1
137 | EXECUTE • Civil |  |  |  | 0 | 15FS+0 |  | N | [5 empty] | 1
138 | Civil: Mobilization & Material Submittals |  |  | 2 | 0 | 137FS+0 | Supervisor+Vendor | N | [5 empty] | 2
139 | Civil: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 138FS+0 | Vendor | N | [5 empty] | 2
140 | Civil: Delivery to Site |  |  | 1 | 0 | 139FS+0 | Vendor+Logistics | N | [5 empty] | 2
141 | Civil: Installation / Execution |  |  | 5 | 0 | 140FS+0 | Vendor+Crew | N | [5 empty] | 2
142 | Civil: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 141FS+0 | Vendor+Supervisor | N | [5 empty] | 2
143 | EXECUTE • Electricals |  |  |  | 0 | 23FS+0 |  | N | [5 empty] | 1
144 | Electricals: Mobilization & Material Submittals |  |  | 2 | 0 | 143FS+0 | Supervisor+Vendor | N | [5 empty] | 2
145 | Electricals: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 144FS+0 | Vendor | N | [5 empty] | 2
146 | Electricals: Delivery to Site |  |  | 1 | 0 | 145FS+0 | Vendor+Logistics | N | [5 empty] | 2
147 | Electricals: Installation / Execution |  |  | 5 | 0 | 146FS+0 | Vendor+Crew | N | [5 empty] | 2
148 | Electricals: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 147FS+0 | Vendor+Supervisor | N | [5 empty] | 2
149 | EXECUTE • Plumbing |  |  |  | 0 | 31FS+0 |  | N | [5 empty] | 1
150 | Plumbing: Mobilization & Material Submittals |  |  | 2 | 0 | 149FS+0 | Supervisor+Vendor | N | [5 empty] | 2
151 | Plumbing: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 150FS+0 | Vendor | N | [5 empty] | 2
152 | Plumbing: Delivery to Site |  |  | 1 | 0 | 151FS+0 | Vendor+Logistics | N | [5 empty] | 2
153 | Plumbing: Installation / Execution |  |  | 5 | 0 | 152FS+0 | Vendor+Crew | N | [5 empty] | 2
154 | Plumbing: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 153FS+0 | Vendor+Supervisor | N | [5 empty] | 2
155 | EXECUTE • Kitchens |  |  |  | 0 | 39FS+0 |  | N | [5 empty] | 1
156 | Kitchens: Mobilization & Material Submittals |  |  | 2 | 0 | 155FS+0 | Supervisor+Vendor | N | [5 empty] | 2
157 | Kitchens: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 156FS+0 | Vendor | N | [5 empty] | 2
158 | Kitchens: Delivery to Site |  |  | 1 | 0 | 157FS+0 | Vendor+Logistics | N | [5 empty] | 2
159 | Kitchens: Installation / Execution |  |  | 5 | 0 | 158FS+0 | Vendor+Crew | N | [5 empty] | 2
160 | Kitchens: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 159FS+0 | Vendor+Supervisor | N | [5 empty] | 2
161 | EXECUTE • Bathrooms |  |  |  | 0 | 47FS+0 |  | N | [5 empty] | 1
162 | Bathrooms: Mobilization & Material Submittals |  |  | 2 | 0 | 161FS+0 | Supervisor+Vendor | N | [5 empty] | 2
163 | Bathrooms: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 162FS+0 | Vendor | N | [5 empty] | 2
164 | Bathrooms: Delivery to Site |  |  | 1 | 0 | 163FS+0 | Vendor+Logistics | N | [5 empty] | 2
165 | Bathrooms: Installation / Execution |  |  | 5 | 0 | 164FS+0 | Vendor+Crew | N | [5 empty] | 2
166 | Bathrooms: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 165FS+0 | Vendor+Supervisor | N | [5 empty] | 2
167 | EXECUTE • Audio |  |  |  | 0 | 55FS+0 |  | N | [5 empty] | 1
168 | Audio: Mobilization & Material Submittals |  |  | 2 | 0 | 167FS+0 | Supervisor+Vendor | N | [5 empty] | 2
169 | Audio: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 168FS+0 | Vendor | N | [5 empty] | 2
170 | Audio: Delivery to Site |  |  | 1 | 0 | 169FS+0 | Vendor+Logistics | N | [5 empty] | 2
171 | Audio: Installation / Execution |  |  | 5 | 0 | 170FS+0 | Vendor+Crew | N | [5 empty] | 2
172 | Audio: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 171FS+0 | Vendor+Supervisor | N | [5 empty] | 2
173 | EXECUTE • Automation |  |  |  | 0 | 63FS+0 |  | N | [5 empty] | 1
174 | Automation: Mobilization & Material Submittals |  |  | 2 | 0 | 173FS+0 | Supervisor+Vendor | N | [5 empty] | 2
175 | Automation: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 174FS+0 | Vendor | N | [5 empty] | 2
176 | Automation: Delivery to Site |  |  | 1 | 0 | 175FS+0 | Vendor+Logistics | N | [5 empty] | 2
177 | Automation: Installation / Execution |  |  | 5 | 0 | 176FS+0 | Vendor+Crew | N | [5 empty] | 2
178 | Automation: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 177FS+0 | Vendor+Supervisor | N | [5 empty] | 2
179 | EXECUTE • Lighting |  |  |  | 0 | 71FS+0 |  | N | [5 empty] | 1
180 | Lighting: Mobilization & Material Submittals |  |  | 2 | 0 | 179FS+0 | Supervisor+Vendor | N | [5 empty] | 2
181 | Lighting: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 180FS+0 | Vendor | N | [5 empty] | 2
182 | Lighting: Delivery to Site |  |  | 1 | 0 | 181FS+0 | Vendor+Logistics | N | [5 empty] | 2
183 | Lighting: Installation / Execution |  |  | 5 | 0 | 182FS+0 | Vendor+Crew | N | [5 empty] | 2
184 | Lighting: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 183FS+0 | Vendor+Supervisor | N | [5 empty] | 2
185 | EXECUTE • HVAC |  |  |  | 0 | 79FS+0 |  | N | [5 empty] | 1
186 | HVAC: Mobilization & Material Submittals |  |  | 2 | 0 | 185FS+0 | Supervisor+Vendor | N | [5 empty] | 2
187 | HVAC: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 186FS+0 | Vendor | N | [5 empty] | 2
188 | HVAC: Delivery to Site |  |  | 1 | 0 | 187FS+0 | Vendor+Logistics | N | [5 empty] | 2
189 | HVAC: Installation / Execution |  |  | 5 | 0 | 188FS+0 | Vendor+Crew | N | [5 empty] | 2
190 | HVAC: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 189FS+0 | Vendor+Supervisor | N | [5 empty] | 2
191 | EXECUTE • Doors & Windows |  |  |  | 0 | 87FS+0 |  | N | [5 empty] | 1
192 | Doors & Windows: Mobilization & Material Submittals |  |  | 2 | 0 | 191FS+0 | Supervisor+Vendor | N | [5 empty] | 2
193 | Doors & Windows: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 192FS+0 | Vendor | N | [5 empty] | 2
194 | Doors & Windows: Delivery to Site |  |  | 1 | 0 | 193FS+0 | Vendor+Logistics | N | [5 empty] | 2
195 | Doors & Windows: Installation / Execution |  |  | 5 | 0 | 194FS+0 | Vendor+Crew | N | [5 empty] | 2
196 | Doors & Windows: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 195FS+0 | Vendor+Supervisor | N | [5 empty] | 2
197 | EXECUTE • Wall Finishes |  |  |  | 0 | 95FS+0 |  | N | [5 empty] | 1
198 | Wall Finishes: Mobilization & Material Submittals |  |  | 2 | 0 | 197FS+0 | Supervisor+Vendor | N | [5 empty] | 2
199 | Wall Finishes: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 198FS+0 | Vendor | N | [5 empty] | 2
200 | Wall Finishes: Delivery to Site |  |  | 1 | 0 | 199FS+0 | Vendor+Logistics | N | [5 empty] | 2
201 | Wall Finishes: Installation / Execution |  |  | 5 | 0 | 200FS+0 | Vendor+Crew | N | [5 empty] | 2
202 | Wall Finishes: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 201FS+0 | Vendor+Supervisor | N | [5 empty] | 2
203 | EXECUTE • Furnishing |  |  |  | 0 | 103FS+0 |  | N | [5 empty] | 1
204 | Furnishing: Mobilization & Material Submittals |  |  | 2 | 0 | 203FS+0 | Supervisor+Vendor | N | [5 empty] | 2
205 | Furnishing: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 204FS+0 | Vendor | N | [5 empty] | 2
206 | Furnishing: Delivery to Site |  |  | 1 | 0 | 205FS+0 | Vendor+Logistics | N | [5 empty] | 2
207 | Furnishing: Installation / Execution |  |  | 5 | 0 | 206FS+0 | Vendor+Crew | N | [5 empty] | 2
208 | Furnishing: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 207FS+0 | Vendor+Supervisor | N | [5 empty] | 2
209 | EXECUTE • Soft Furnishing |  |  |  | 0 | 111FS+0 |  | N | [5 empty] | 1
210 | Soft Furnishing: Mobilization & Material Submittals |  |  | 2 | 0 | 209FS+0 | Supervisor+Vendor | N | [5 empty] | 2
211 | Soft Furnishing: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 210FS+0 | Vendor | N | [5 empty] | 2
212 | Soft Furnishing: Delivery to Site |  |  | 1 | 0 | 211FS+0 | Vendor+Logistics | N | [5 empty] | 2
213 | Soft Furnishing: Installation / Execution |  |  | 5 | 0 | 212FS+0 | Vendor+Crew | N | [5 empty] | 2
214 | Soft Furnishing: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 213FS+0 | Vendor+Supervisor | N | [5 empty] | 2
215 | EXECUTE • Appliances |  |  |  | 0 | 119FS+0 |  | N | [5 empty] | 1
216 | Appliances: Mobilization & Material Submittals |  |  | 2 | 0 | 215FS+0 | Supervisor+Vendor | N | [5 empty] | 2
217 | Appliances: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 216FS+0 | Vendor | N | [5 empty] | 2
218 | Appliances: Delivery to Site |  |  | 1 | 0 | 217FS+0 | Vendor+Logistics | N | [5 empty] | 2
219 | Appliances: Installation / Execution |  |  | 5 | 0 | 218FS+0 | Vendor+Crew | N | [5 empty] | 2
220 | Appliances: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 219FS+0 | Vendor+Supervisor | N | [5 empty] | 2
221 | EXECUTE • Flooring |  |  |  | 0 | 127FS+0 |  | N | [5 empty] | 1
222 | Flooring: Mobilization & Material Submittals |  |  | 2 | 0 | 221FS+0 | Supervisor+Vendor | N | [5 empty] | 2
223 | Flooring: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 222FS+0 | Vendor | N | [5 empty] | 2
224 | Flooring: Delivery to Site |  |  | 1 | 0 | 223FS+0 | Vendor+Logistics | N | [5 empty] | 2
225 | Flooring: Installation / Execution |  |  | 5 | 0 | 224FS+0 | Vendor+Crew | N | [5 empty] | 2
226 | Flooring: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 225FS+0 | Vendor+Supervisor | N | [5 empty] | 2
227 | EXECUTE • Carpentry |  |  |  | 0 | 135FS+0 |  | N | [5 empty] | 1
228 | Carpentry: Mobilization & Material Submittals |  |  | 2 | 0 | 227FS+0 | Supervisor+Vendor | N | [5 empty] | 2
229 | Carpentry: Fabrication / Off‑site Prep (if applicable) |  |  | 7 | 0 | 228FS+0 | Vendor | N | [5 empty] | 2
230 | Carpentry: Delivery to Site |  |  | 1 | 0 | 229FS+0 | Vendor+Logistics | N | [5 empty] | 2
231 | Carpentry: Installation / Execution |  |  | 5 | 0 | 230FS+0 | Vendor+Crew | N | [5 empty] | 2
232 | Carpentry: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 231FS+0 | Vendor+Supervisor | N | [5 empty] | 2
| LINK • Flooring waits for Civil |  |  |  | 0 | 142FS+0 |  | N | [5 empty] | 2
| LINK • Wall Finishes wait for Civil |  |  |  | 0 | 142FS+0 |  | N | [5 empty] | 2
| LINK • Doors & Windows wait for Civil |  |  |  | 0 | 142FS+0 |  | N | [5 empty] | 2
| LINK • Carpentry waits for Civil |  |  |  | 0 | 142FS+0 |  | N | [5 empty] | 2
| LINK • Lighting after Electricals |  |  |  | 0 | 148FS+0 |  | N | [5 empty] | 2
| LINK • Automation after Electricals |  |  |  | 0 | 148FS+0 |  | N | [5 empty] | 2
| LINK • Audio after Electricals |  |  |  | 0 | 148FS+0 |  | N | [5 empty] | 2
| LINK • Kitchens after Plumbing |  |  |  | 0 | 154FS+0 |  | N | [5 empty] | 2
| LINK • Bathrooms after Plumbing |  |  |  | 0 | 154FS+0 |  | N | [5 empty] | 2
| LINK • Appliances after Kitchens & Electricals |  |  |  | 0 | 160FS+0,148FS+0 |  | N | [5 empty] | 2
233 | PHASE • Closeout & Handover |  |  |  | 0 |  |  | N | [5 empty] | 1
234 | All Trades Complete – Declaration |  |  | 0 | 0 | 142FS+0,148FS+0,154FS+0,160FS+0,166FS+0,172FS+0,178FS+0,184FS+0,190FS+0,196FS+0,202FS+0,208FS+0,214FS+0,220FS+0,226FS+0,232FS+0 | Supervisor | N | [5 empty] | 2
235 | Snagging / Punch List |  |  | 3 | 0 | 234FS+0 | Designer+Supervisor | N | [5 empty] | 2
236 | Rectification of Snags |  |  | 5 | 0 | 235FS+0 | Relevant Vendors | N | [5 empty] | 2
237 | Client Demo & Acceptance |  |  | 1 | 0 | 236FS+0 | Client | Y | [5 empty] | 2
238 | Practical Completion / Handover |  |  | 1 | 0 | 237FS+0 | Client | Y | [5 empty] | 2
239 | As‑Built Docs & O&M Manuals |  |  | 5 | 0 | 238FS+0 | Designer | N | [5 empty] | 2