## Gantt
ID | Name | Start | Finish | Duration | % Complete | Predecessor | Resource Names | Approval Required | Materials | Owner | Target Start | Target Finish | Remarks | Outline Level | Color
1 | Project Kickoff | 2024-01-01 | 2024-01-01 | 1 | 100 |  | PM Team | N | Project Materials | Hiremath | 2024-01-01 | 2024-01-01 | Initial project setup | 1 | #4EA623
2 | Design Phase | 2024-01-02 | 2024-01-08 | 7 | 75 | 1FS+0 | Designer, Architect | Y | Design Software | Design Team | 2024-01-02 | 2024-01-08 | Complete soil testing | 2 | #A65023
3 | Client Approval | 2024-01-09 | 2024-01-11 | 3 | 50 | 2FS+0 | Client Relations | Y | Client Retain | Await client payment | 2024-01-09 | 2024-01-11 | Awaiting client payment | 2 | #5A5623
4 | Construction | 2024-01-12 | 2024-01-26 | 15 | 20 | 3FS+0 | Construction M | N | Wood, Paint, Construction Materials | Main contractor | 2024-01-12 | 2024-01-26 | Final quality check | 1 | #FE0341
5 | Final Inspect | 2024-01-26 | 2024-01-27 | 2 | 0 | 4SS+0 | Inspector | Y | Quality Team |  | 2024-01-26 | 2024-01-27 | Final quality check | 2