## Tasks
ID | Name | Start | Finish | Duration | % Complete | Predecessors | Resource Names | Status | Priority | Approval Required | Materials | Owner | Target Start | Target Finish | Remarks | Outline Level | Color
1 | PHASE • Design & Approvals |  |  |  | 0 |  |  |  | high | N | [5 empty] | 1
2 | Client Brief & Scope | 2025-06-01 | 2025-06-01 | 1 | 100 |  | Hiremaths | Complete | medium | N | [5 empty] | 2
3 | Schematic Drawings (Overall) | 2025-06-09 | 2025-11-15 | 180 | 70 | 2(FS) | SHV | Started | medium | N | [5 empty] | 2
4 | Working Drawings (Overall) | 2025-10-11 | 2025-12-05 | 7 | 10 | 3(FS) | STARC | Started | medium | N | [5 empty] | 2
5 | Finishes Board & Samples (Overall) | 2025-07-04 | 2025-09-06 | 3 | 100 | 3(FS) | SHV | Complete | medium | Y | [5 empty] | 2
6 | Client Sign‑off (Drawings & Finishes) | 2025-10-15 | 2025-09-06 | 1 | 30 | 4(FS),5(FS) | Hiremaths | Started | high | Y | [5 empty] | 2
7 | PHASE • Vendor Evaluation → Quotes → Finalisation → Work Orders |  |  |  | 0 |  |  | Started | medium | N | [5 empty] | 1
8 | PACKAGE • Civil |  |  |  | 0 | 6(FS) |  | Complete | medium | N | [5 empty] | 1
9 | Civil: Vendor Evaluation (shortlist) | 2025-06-30 | 2025-09-18 | 3 | 0 | 8(FS) | Designer | Complete | medium | N | [5 empty] | 2
10 | Civil: RFQs Issued | 2025-06-13 | 2025-06-13 | 2 | 0 | 10(FS) | Designer | not_started | medium | N | [5 empty] | 2
11 | Civil: Vendor Finalisation | 2025-06-25 | 2025-06-25 | 1 | 0 | 13(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
12 | Civil: Work Order / PO Release | 2025-09-26 | 2025-11-29 | 1 | 0 | 14(FS) | Designer | not_started | medium | Y | [5 empty] | 2
13 | PACKAGE • Electricals |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
14 | Electricals: Vendor Evaluation(shortlist) | 2025-10-20 | 2025-10-21 | 3 | 0 | 16(FS) | Designer | not_started | medium | N | [5 empty] | 2
15 | Electricals: RFQs Issued | 2025-10-23 | 2025-10-25 | 2 | 0 | 18(FS) | Designer | not_started | medium | N | [5 empty] | 2
16 | Electricals: Vendor Finalisation | 2025-11-10 | 2025-11-10 | 1 | 0 | 21(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
17 | Electricals: Work Order / PO Release | 2025-11-17 | 2025-11-17 | 1 | 0 | 22(FS) | Designer | not_started | medium | Y | [5 empty] | 2
18 | PACKAGE • Plumbing |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
19 | Plumbing: Vendor Evaluation (shortlist) | 2025-11-08 | 2025-08-11 | 3 | 0 | 24(FS) | Designer | not_started | medium | N | [5 empty] | 2
20 | Plumbing: RFQs Issued | 2025-11-13 | 2025-11-13 | 2 | 0 | 26(FS) | Designer | not_started | medium | N | [5 empty] | 2
21 | Plumbing: Vendor Finalisation | 2025-11-15 | 2025-11-15 | 1 | 0 | 29(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
22 | Plumbing: Work Order / PO Release | 2025-11-26 | 2025-11-29 | 1 | 0 | 30(FS) | Designer | not_started | medium | Y | [5 empty] | 2
23 | PACKAGE • Kitchens |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
24 | Kitchens: Vendor Evaluation (shortlist) | 2025-08-25 | 2025-08-25 | 3 | 0 | 32(FS) | Designer | not_started | medium | N | [5 empty] | 2
25 | Kitchens: RFQs Issued | 2025-08-25 | 2025-08-25 | 2 | 0 | 34(FS) | Designer | not_started | medium | N | [5 empty] | 2
26 | Kitchens: Vendor Finalisation | 2025-10-15 | 2025-10-15 | 1 | 0 | 37(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
27 | Kitchens: Work Order / PO Release | 2025-10-30 | 2025-10-30 | 1 | 0 | 38(FS) | Designer | not_started | medium | Y | [5 empty] | 2
28 | PACKAGE • Sanitary Fittings |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
29 | Bathrooms: Vendor Evaluation (shortlist) | 2025-10-13 | 2025-10-13 | 3 | 0 | 40(FS) | Designer | not_started | medium | N | [5 empty] | 2
30 | Bathrooms: RFQs Issued | 2025-10-15 | 2025-10-15 | 2 | 0 | 42(FS) | Designer | not_started | medium | N | [5 empty] | 2
31 | Bathrooms: Vendor Finalisation | 2025-11-11 | 2025-11-11 | 1 | 0 | 45(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
32 | Bathrooms: Work Order / PO Release | 2025-11-11 | 2025-11-11 | 1 | 0 | 46(FS) | Designer | not_started | medium | Y | [5 empty] | 2
33 | PACKAGE • Audio |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
34 | Audio: Vendor Evaluation (shortlist) | 2025-08-12 | 2025-08-12 | 3 | 0 | 48(FS) | Designer | not_started | medium | N | [5 empty] | 2
35 | Audio: RFQs Issued | 2025-08-09 | 2025-08-09 | 2 | 0 | 50(FS) | Designer | not_started | medium | N | [5 empty] | 2
36 | Audio: Vendor Finalisation | 2025-08-09 | 2025-08-09 | 1 | 0 | 53(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
37 | Audio: Work Order / PO Release | 2025-08-21 | 2025-08-21 | 1 | 0 | 54(FS) | Designer | not_started | medium | Y | [5 empty] | 2
38 | PACKAGE • Automation |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
39 | Automation: Vendor Evaluation (shortlist) | 2025-10-11 | 2025-10-11 | 3 | 0 | 56(FS) | Designer | not_started | medium | N | [5 empty] | 2
40 | Automation: RFQs Issued | 2025-10-11 | 2025-10-11 | 2 | 0 | 58(FS) | Designer | not_started | medium | N | [5 empty] | 2
41 | Automation: Vendor Finalisation | 2025-10-17 | 2025-10-17 | 1 | 0 | 61(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
42 | Automation: Work Order / PO Release | 2025-11-17 | 2025-11-17 | 1 | 0 | 62(FS) | Designer | not_started | medium | Y | [5 empty] | 2
43 | PACKAGE • Lighting |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
44 | Lighting: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | 3 | 0 | 64(FS) | Designer | not_started | medium | N | [5 empty] | 2
45 | Lighting: RFQs Issued | 2025-10-09 | 2025-10-09 | 2 | 0 | 66(FS) | Designer | not_started | medium | N | [5 empty] | 2
46 | Lighting: Vendor Finalisation | 2025-10-10 | 2025-10-10 | 1 | 0 | 69(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
47 | Lighting: Work Order / PO Release | 2025-11-17 | 2025-11-17 | 1 | 0 | 70(FS) | Designer | not_started | medium | Y | [5 empty] | 2
48 | PACKAGE • HVAC |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
49 | HVAC: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | 3 | 0 | 72(FS) | Designer | not_started | medium | N | [5 empty] | 2
50 | HVAC: RFQs Issued | 2025-10-09 | 2025-10-09 | 2 | 0 | 74(FS) | Designer | not_started | medium | N | [5 empty] | 2
51 | HVAC: Vendor Finalisation | 2025-10-10 | 2025-10-10 | 1 | 0 | 77(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
52 | HVAC: Work Order / PO Release | 2025-11-17 | 2025-11-22 | 1 | 0 | 78(FS) | Designer | not_started | medium | Y | [5 empty] | 2
53 | PACKAGE • Windows |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
54 | Doors & Windows: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | 3 | 0 | 80(FS) | Designer | not_started | medium | N | [5 empty] | 2
55 | Doors & Windows: RFQs Issued | 2025-08-28 | 2025-08-28 | 2 | 0 | 82(FS) | Designer | not_started | medium | N | [5 empty] | 2
56 | Doors & Windows: Vendor Finalisation | 2025-10-24 | 2025-10-24 | 1 | 0 | 85(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
57 | Doors & Windows: Work Order / PO Release | 2025-11-17 | 2025-11-17 | 1 | 0 | 86(FS) | Designer | not_started | medium | Y | [5 empty] | 2
58 | PACKAGE • Wall Finishes |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
59 | Wall Finishes: Vendor Evaluation (shortlist) | 2025-08-08 | 2025-08-08 | 3 | 0 | 88(FS) | Designer | not_started | medium | N | [5 empty] | 2
60 | Wall Finishes: RFQs Issued | 2025-12-05 | 2025-12-05 | 2 | 0 | 90(FS) | Designer | not_started | medium | N | [5 empty] | 2
61 | Wall Finishes: Vendor Finalisation | 2026-01-15 | 2026-01-15 | 1 | 0 | 93(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
62 | Wall Finishes: Work Order / PO Release | 2026-01-30 | 2026-01-30 | 1 | 0 | 94(FS) | Designer | not_started | medium | Y | [5 empty] | 2
63 | PACKAGE - FURNITURE |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
64 | Furnishing: Vendor Evaluation (shortlist) | 2026-01-10 | 2026-01-10 | 3 | 0 | 96(FS) | Designer | not_started | medium | N | [5 empty] | 2
65 | Furnishing: RFQs Issued | 2026-01-15 | 2026-01-15 | 2 | 0 | 98(FS) | Designer | not_started | medium | N | [5 empty] | 2
66 | Furnishing: Vendor Finalisation | 2026-02-06 | 2026-02-06 | 1 | 0 | 101(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
67 | Furnishing: Work Order / PO Release | 2026-02-13 | 2026-02-13 | 1 | 0 | 102(FS) | Designer | not_started | medium | Y | [5 empty] | 2
68 | PACKAGE • Soft Furnishing |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
69 | Soft Furnishing: Vendor Evaluation (shortlist) | 2026-02-22 | 2026-02-22 | 3 | 0 | 104(FS) | Designer | not_started | medium | N | [5 empty] | 2
70 | Soft Furnishing: RFQs Issued | 2026-02-26 | 2026-02-26 | 2 | 0 | 106(FS) | Designer | not_started | medium | N | [5 empty] | 2
71 | Soft Furnishing: Vendor Finalisation | 2026-03-06 | 2026-03-06 | 1 | 0 | 109(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
72 | Soft Furnishing: Work Order / PO Release | 2026-03-12 | 2026-03-12 | 1 | 0 | 110(FS) | Designer | not_started | medium | Y | [5 empty] | 2
73 | PACKAGE • Appliances |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
74 | Appliances: Vendor Evaluation (shortlist) | 2025-11-13 | 2025-11-13 | 3 | 0 | 112(FS) | Designer | not_started | medium | N | [5 empty] | 2
75 | Appliances: RFQs Issued | 2025-11-18 | 2025-11-18 | 2 | 0 | 114(FS) | Designer | not_started | medium | N | [5 empty] | 2
76 | Appliances: Vendor Finalisation | 2025-12-10 | 2025-12-10 | 1 | 0 | 117(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
77 | Appliances: Work Order / PO Release | 2025-12-15 | 2025-12-15 | 1 | 0 | 118(FS) | Designer | not_started | medium | Y | [5 empty] | 2
78 | PACKAGE • Flooring |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
79 | Flooring: Vendor Evaluation (shortlist) | 2025-08-16 | 2025-08-16 | 3 | 0 | 120(FS) | Designer | not_started | medium | N | [5 empty] | 2
80 | Flooring: RFQs Issued | 2025-08-16 | 2025-08-16 | 2 | 0 | 122(FS) | Designer | not_started | medium | N | [5 empty] | 2
81 | Flooring: Vendor Finalisation | 2025-11-15 | 2025-11-15 | 1 | 0 | 125(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
82 | Flooring: Work Order / PO Release | 2025-11-17 | 2025-11-17 | 1 | 0 | 126(FS) | Designer | not_started | medium | Y | [5 empty] | 2
83 | PACKAGE • Carpentry |  |  |  | 0 | 6(FS) |  | not_started | medium | N | [5 empty] | 1
84 | Carpentry: Vendor Evaluation (shortlist) | 2025-09-25 | 2025-10-05 | 3 | 0 | 128(FS) | Designer | not_started | medium | N | [5 empty] | 2
85 | Carpentry: RFQs Issued | 2025-11-29 | 2025-11-29 | 2 | 0 | 130(FS) | Designer | not_started | medium | N | [5 empty] | 2
86 | Carpentry: Vendor Finalisation | 2025-11-30 | 2025-12-04 | 1 | 0 | 133(FS) | Designer+Client | not_started | medium | Y | [5 empty] | 2
87 | Carpentry: Work Order / PO Release | 2025-12-05 | 2025-12-05 | 1 | 0 | 134(FS) | Designer | not_started | medium | Y | [5 empty] | 2
88 | PHASE • Execution (Category-wise) |  |  |  | 0 |  |  | not_started | medium | N | [5 empty] | 1
89 | EXECUTE • Civil |  |  |  | 0 | 15(FS) |  | not_started | medium | N | [5 empty] | 1
90 | Civil: Drawings plans & elevations | 2025-03-20 | 2025-03-24
91 | Civil: Drawings checking | 2025-03-25 | 2025-09-15
92 | Civil: Drawings Revisions | 2025-09-16 | 2025-09-20
93 | Civil: Fabrication / Off‑site Prep (if applicable) |  |  | 2 | 0 | 137(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
94 | MaterialDelivery on site | 2025-07-02 | 2025-07-07 | 7 | 0 | 138(FS) | Vendor | not_started | medium | N | [5 empty] | 2
95 | Civil: Installation / Execution | 2025-07-02 | 2025-12-10 | 5 | 0 | 140(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
96 | Civil: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 141(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
97 | EXECUTE • Plumbing |  |  |  | 0 | 31(FS) |  | not_started | medium | N | [5 empty] | 1
98 | Music Room: Drawings plans & elevations | 2025-11-25 | 2025-12-01
99 | Master Bedroom: Drawings Plans & Elevations | 2025-11-28 | 2025-12-01
100 | Chitra's Room: Drawings Plans & elevations | 2025-11-30 | 2025-12-01
101 | Powder Room: Drawings Plans & Elevations | 2025-11-30 | 2025-12-01
102 | All Bathrooms: Drawings checking | 2025-12-02 | 2025-12-04
103 | All Bathrooms: Revisions | 2025-12-05 | 2025-12-06
104 | Plumbing: Fabrication / Off‑site Prep (if applicable)
105 | Plumbing: Material delivery to site | 2025-12-08 | 2025-12-13 | 2 | 0 | 149(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
106 | Plumbing: Execution | 2025-12-08 | 2025-01-05 | 5 | 0 | 152(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
107 | Plumbing: Installation | 2026-05-08 | 2026-05-17
108 | Plumbing: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | 2 | 0 | 153(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
109 | EXECUTE • Kitchens |  |  |  | 0 | 39(FS) |  | not_started | medium | N | [5 empty] | 1
110 | Kitchen: Drawings Plans & elevations
111 | Kitchen: Drawings checking
112 | Kitchen: Drawings Revisions
113 | Kitchens: Fabrication / Off‑site Prep (if applicable)
114 | Kitchens: Material delivery to site |  |  | 2 | 0 | 155(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
115 | Kitchens: Installation / Execution |  |  | 5 | 0 | 158(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
116 | Kitchens: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 159(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
117 | EXECUTE • Bathrooms |  |  |  | 0 | 47(FS) |  | not_started | medium | N | [5 empty] | 1
118 | Music Room: Drawings plans & elevations | 2025-11-25 | 2025-12-05
119 | Master Bedroom: Drawings Plans & Elevations | 2025-11-28 | 2025-12-05
120 | Chitra's Room: Drawings Plans & elevations | 2025-11-30 | 2025-12-05
121 | Powder Room: Drawings Plans & Elevations | 2025-11-30 | 2025-12-05
122 | All Bathrooms: Drawings checking | 2025-12-05 | 2025-12-08
123 | All Bathrooms: Revisions | 2025-12-09 | 2025-12-12
124 | Bathrooms: Fabrication / Off‑site Prep (if applicable)
125 | Bathrooms: Finishing Material delivery to site | 2025-12-08 | 2025-12-13 | 2 | 0 | 161(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
126 | Bathrooms: Execution | 2026-01-06 | 2026-02-06 | 5 | 0 | 164(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
127 | Bathrooms: Installation | 2026-05-08 | 2026-05-17
128 | Bathrooms: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | 2 | 0 | 165(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
129 | EXECUTE • Audio |  |  |  | 0 | 55(FS) |  | not_started | medium | N | [5 empty] | 1
130 | Audio: shop Drawings
131 | Audio: Drawings checking
132 | Audio: Revisions
133 | Audio: Fabrication / Off‑site Prep (if applicable)
134 | Audio: Material delivery to Site |  |  | 2 | 0 | 167(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
135 | Audio: Execution |  |  | 5 | 0 | 170(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
136 | Audio: Installation
137 | Audio: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 171(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
138 | EXECUTE • Automation + Electricals + lighting |  |  |  | 0 | 63(FS) |  | not_started | medium | N | [5 empty] | 1
139 | AEL: shop drawings | 2025-11-27 | 2025-12-02
140 | AEL: Drawings checking | 2025-12-03 | 2025-12-05
141 | AEL: Revisions | 2025-12-05 | 2025-12-08
142 | AEL: Fabrication / Off‑site Prep (if applicable)
143 | Automation: Material delivery to site | 2026-01-27 | 2026-01-01 | 2 | 0 | 173(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
144 | AEL: Execution | 2025-12-02 | 2026-01-02 | 5 | 0 | 176(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
145 | AEL: Installation | 2026-05-08 | 2026-05-17
146 | AEL: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | 2 | 0 | 177(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
147 | EXECUTE • HVAC |  |  |  | 0 | 79(FS) |  | not_started | medium | N | [5 empty] | 1
148 | HVAC: shop drawings | 2025-11-09 | 2025-11-11
149 | HVAC: Drawings checking | 2025-11-11 | 2025-11-11
150 | HVAC: Revisions | 2025-11-11 | 2025-11-11
151 | HVAC: Fabrication / Off‑site Prep (if applicable)
152 | HVAC:Material delivery to site |  |  | 2 | 0 | 185(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
153 | HVAC: Execution | 2025-12-02 | 2026-01-02 | 5 | 0 | 188(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
154 | HVAC: Installation | 2026-05-08 | 2026-05-17
155 | HVAC: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | 2 | 0 | 189(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
156 | EXECUTE • Windows |  |  |  | 0 | 87(FS) |  | not_started | medium | N | [5 empty] | 1
157 | Windows: shop drawings
158 | Windows: Drawings checking
159 | Windows: Revisions
160 | Windows: Fabrication / Off‑site Prep (if applicable)
161 | Windows: Material delivery on site |  |  | 2 | 0 | 191(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
162 | Windows: Installation / Execution |  |  | 5 | 0 | 194(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
163 | Windows: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 195(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
164 | EXECUTE • Wall Finishes |  |  |  | 0 | 95(FS) |  | not_started | medium | N | [5 empty] | 1
165 | Wall Finishes: Material delivery on site- plaster of paris | 2025-12-05 | 2025-12-06 | 2 | 0 | 197(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
166 | Wall Finishes: Fabrication / Off‑site Prep (if applicable)
167 | Wall Finishes: Material delivery on site- Wall paper
168 | Wall Finishes: Execution - Plaster of Paris works | 2025-12-07 | 2026-02-10
169 | Wall Finishes: Installation / Execution - Wall paper/paint/limewash |  |  | 5 | 0 | 200(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
170 | Wall Finishes: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 201(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
171 | EXECUTE • Furnishing |  |  |  | 0 | 103(FS) |  | not_started | medium | N | [5 empty] | 1
172 | Furnishing: Fabrication / Off‑site Prep (if applicable)
173 | Furnishing: Material delivery on site |  |  | 2 | 0 | 203(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
174 | Furnishing: Installation / Execution |  |  | 5 | 0 | 206(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
175 | Furnishing: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 207(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
176 | EXECUTE • Soft Furnishing |  |  |  | 0 | 111(FS) |  | not_started | medium | N | [5 empty] | 1
177 | Soft Furnishing: Fabrication / Off‑site Prep (if applicable)
178 | Soft Furnishing: Material delivery on site |  |  | 2 | 0 | 209(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
179 | Soft Furnishing: Installation / Execution |  |  | 5 | 0 | 212(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
180 | Soft Furnishing: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 213(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
181 | EXECUTE • Appliances |  |  |  | 0 | 119(FS) |  | not_started | medium | N | [5 empty] | 1
182 | Appliances: Fabrication / Off‑site Prep (if applicable)
183 | Appliances: Material delivery on site |  |  | 2 | 0 | 215(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
184 | Appliances: Installation / Execution |  |  | 5 | 0 | 218(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
185 | Appliances: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 219(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
186 | EXECUTE • Flooring |  |  |  | 0 | 127(FS) |  | not_started | medium | N | [5 empty] | 1
187 | Flooring: drawings plan | 2025-12-04 | 2025-12-08
188 | Flooring: Drawings checking | 2025-12-09 | 2025-12-11
189 | Flooring: Revisions | 2025-12-12 | 2025-12-12
190 | Flooring: Fabrication / Off‑site Prep (if applicable)
191 | Flooring: Material delivery on site |  |  | 2 | 0 | 221(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
192 | Flooring: Installation / Execution |  |  | 5 | 0 | 224(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
193 | Flooring: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 225(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
194 | EXECUTE • Carpentry |  |  |  | 0 | 135(FS) |  | not_started | medium | N | [5 empty] | 1
195 | Windows: shop drawings fixed furniture sketches | 2025-11-05 | 2025-11-15
196 | Windows: shop drawings fixed furniture: checking | 2025-11-17 | 2025-11-17
197 | Windows: shop drawings fixed furniture: revisions | 2025-11-20 | 2025-11-28
198 | Carpentry: Material delivery at workshop | 2025-12-05 | 2025-12-09 | 2 | 0 | 227(FS) | Supervisor+Vendor | not_started | medium | N | [5 empty] | 2
199 | Carpentry: Fabrication / Off‑site Prep (if applicable) | 2025-12-11 | 2026-03-20 | 7 | 0 | 228(FS) | Vendor | not_started | medium | N | [5 empty] | 2
200 | Carpentry: Installation / Execution | 2026-03-23 | 2026-04-23 | 5 | 0 | 230(FS) | Vendor+Crew | not_started | medium | N | [5 empty] | 2
201 | Carpentry: Testing & Commissioning / QA‑QC |  |  | 2 | 0 | 231(FS) | Vendor+Supervisor | not_started | medium | N | [5 empty] | 2
202 | LINK • Flooring waits for Civil |  |  |  | 0 | 142(FS) |  | not_started | medium | N | [5 empty] | 2
203 | LINK • Wall Finishes wait for Civil |  |  |  | 0 | 142(FS) |  | not_started | medium | N | [5 empty] | 2
204 | LINK • Doors & Windows wait for Civil |  |  |  | 0 | 142(FS) |  | not_started | medium | N | [5 empty] | 2
205 | LINK • Carpentry waits for Civil |  |  |  | 0 | 142(FS) |  | not_started | medium | N | [5 empty] | 2
206 | LINK • Lighting after Electricals |  |  |  | 0 | 148(FS) |  | not_started | medium | N | [5 empty] | 2
207 | LINK • Automation after Electricals |  |  |  | 0 | 148(FS) |  | not_started | medium | N | [5 empty] | 2
208 | LINK • Audio after Electricals |  |  |  | 0 | 148(FS) |  | not_started | medium | N | [5 empty] | 2
209 | LINK • Kitchens after Plumbing |  |  |  | 0 | 154(FS) |  | not_started | medium | N | [5 empty] | 2
210 | LINK • Bathrooms after Plumbing |  |  |  | 0 | 154(FS) |  | not_started | medium | N | [5 empty] | 2
211 | LINK • Appliances after Kitchens & Electricals |  |  |  | 0 | 160(FS),148(FS) |  | not_started | medium | N | [5 empty] | 2
212 | PHASE • Closeout & Handover |  |  |  | 0 |  |  | not_started | medium | N | [5 empty] | 1
213 | All Trades Complete – Declaration |  |  | 0 | 0 | 142(FS),148(FS),154(FS),160(FS),166(FS),172(FS),178(FS),184(FS),190(FS),196(FS),202(FS),208(FS),214(FS),220(FS),226(FS),232(FS) | Supervisor | not_started | medium | N | [5 empty] | 2
214 | Snagging / Punch List |  |  | 3 | 0 | 234(FS) | Designer+Supervisor | not_started | medium | N | [5 empty] | 2
215 | Rectification of Snags |  |  | 5 | 0 | 235(FS) | Relevant Vendors | not_started | medium | N | [5 empty] | 2
216 | Client Demo & Acceptance |  |  | 1 | 0 | 236(FS) | Client | not_started | medium | Y | [5 empty] | 2
217 | Practical Completion / Handover |  |  | 1 | 0 | 237(FS) | Client | not_started | medium | Y | [5 empty] | 2
218 | As‑Built Docs & O&M Manuals |  |  | 5 | 0 | 238(FS) | Designer | not_started | medium | N | [5 empty] | 2

## Instructions
PixelCraft Designer - Interior Design Gantt Chart Template
QUICK START GUIDE
1. Your template contains 249 pre-defined tasks organized by phases and packages
2. Enter Start Date in column C (format: YYYY-MM-DD or use Ctrl+; for today)
3. Duration (column E) is pre-filled - adjust as needed
4. Dependencies (column G) are pre-configured in format: TaskID(Type)
TASK ORGANIZATION
• PHASE • Design & Approvals - Initial design phase (6 tasks)
• PHASE • Vendor Evaluation → Quotes → Finalisation → Work Orders
• 20 PACKAGE categories: Civil, Electricals, Plumbing, Kitchens, Bathrooms, etc.
• Each package has 7 sequential tasks: Evaluation → Meetings → RFQs → Quotes → Comparison → Finalisation → Work Order
COLUMN REFERENCE
Column | Description | How to Use
ID | Task identifier (1-249) | Pre-filled, do not change
Name | Task name | Pre-filled with real project tasks
Start | Start date | Enter as YYYY-MM-DD (e.g., 2024-01-15)
Finish | End date | Leave blank - will calculate when imported
Duration | Working days | Pre-filled, adjust as needed
% Complete | Progress (0-100) | Update as work progresses
Predecessors | Dependencies | Pre-configured: TaskID(Type) format
Resource Names | Assigned team | Designer, Client, Vendor, etc.
Status | Current status | not_started, in_progress, completed, blocked
Priority | Task priority | low, medium, high
Approval Required | Needs approval? | Y or N
Materials | Required materials | Optional
Owner | Task owner | Optional
Target Start | Planned start | Optional - for planning
Target Finish | Planned finish | Optional - for planning
Remarks | Notes | Additional information
Outline Level | Hierarchy | 1=Phase/Package, 2=Task
Color | Task color | Optional hex code
DEPENDENCY TYPES
Format | Type | Meaning
TaskID(FS) | Finish-to-Start | Task finishes before this starts
TaskID(SS) | Start-to-Start | Task starts before this starts
TaskID(FF) | Finish-to-Finish | Task finishes before this finishes
TaskID(SF) | Start-to-Finish | Task starts before this finishes
With lag | Add delay | 2(FS)+3 = Wait 3 days after Task 2
Multiple | Comma-separated | 4(FS),5(FS) = Wait for both tasks
AFTER IMPORT TO PIXELCRAFT DESIGNER
• System calculates Finish dates automatically (Start + Duration - 1)
• Critical Path Analysis identifies tasks that cannot be delayed
• Project duration and critical percentage are displayed
• Circular dependencies are detected and prevented
• Download updated schedule anytime with current progress