## Designer Schedule
# | Task Name | Start Date | End Date | Status | Remarks | DB_ID | Schedule_ID | Priority | Duration | Task ID | Assigned To
1 | PHASE • Design & Approvals |  |  |  |  | a84acca7-67e8-49a2-a2ff-d057d6a9cce0 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 1
2 | Client Brief & Scope | 2025-06-01 | 2025-06-01 | Completed |  | de6eaf6c-2b92-415b-8dbc-14ac3c987cd2 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 2
3 | Schematic Drawings (Overall) | 2025-06-09 | 2025-12-15 | Incomplete |  | d1c72a40-e226-42bf-b043-c4a5991a3167 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 180.00 | 3
4 | Working Drawings (Overall) | 2025-10-11 | 2025-12-20 | Incomplete |  | 6ddd7fd4-4e68-4a75-a7ac-e3244450c275 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 7.00 | 4
5 | Finishes Board & Samples (Overall) | 2025-07-04 | 2025-09-06 | Completed |  | 604c395a-c291-4379-ae4c-9f9abe731af5 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 5
6 | Client Sign‑off (Drawings & Finishes) | 2025-10-15 | 2025-12-18 | Incomplete |  | dc38a686-c5e3-4b33-ac07-d923497321d9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 6
7 | PHASE • Vendor Evaluation → Quotes → Finalisation → Work Orders |  |  |  |  | 33599efb-02d2-4577-bb55-26aa5bf4122f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 7
8 | PACKAGE • Civil |  |  |  |  | 9fe1d400-835e-45ff-9ac5-6cd26b9098cd | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 8
9 | Civil: Vendor Evaluation (shortlist) | 2025-06-30 | 2025-09-18 | Completed |  | 5fe70923-e178-4e2d-9a88-d5d610e8736f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 9
10 | Civil: RFQs Issued | 2025-06-13 | 2025-06-13 | Completed |  | cf8ccdd4-bd55-48d8-9c52-eca094ab356c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 10
11 | Civil: Vendor Finalisation | 2025-06-25 | 2025-06-25 | Completed |  | 34523f32-39b9-4175-8578-ff8bb1d25209 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 11
12 | Civil: Work Order / PO Release | 2025-09-26 | 2025-11-29 | Completed |  | 59c5e4fb-2b7a-49b6-ae09-5d8ab662526d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 12
13 | PACKAGE • Electricals |  |  |  |  | c37407e6-3d73-4c7c-8272-386df8e337d1 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 13
14 | Electricals: Vendor Evaluation(shortlist) | 2025-10-20 | 2025-10-21 | Completed |  | e0a83683-2037-4450-8387-934d30e60cdd | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 14
15 | Electricals: RFQs Issued | 2025-10-23 | 2025-10-25 | Completed |  | 96387a37-50a9-427f-864a-7a9065b81362 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 15
16 | Electricals: Vendor Finalisation | 2025-11-10 | 2025-11-10 | Completed |  | 438d6597-1585-429e-ad19-da6de92be038 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 16
17 | Electricals: Work Order / PO Release | 2025-11-17 | 2025-11-17 | Completed |  | bf2f09ee-f358-4e2c-bfaf-8ad6d7808936 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 17
18 | PACKAGE • Plumbing |  |  |  |  | cb4e4472-9dd5-490b-b419-f2ab6f6d9bf4 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 18
19 | Plumbing: Vendor Evaluation (shortlist) | 2025-11-08 | 2025-08-11 | Completed |  | cbdd57c8-7b67-4bbe-8bf5-96824d5b9ca7 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 19
20 | Plumbing: RFQs Issued | 2025-11-13 | 2025-11-13 | Completed |  | 178993bb-d648-404d-b41f-c2412cda9fdc | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 20
21 | Plumbing: Vendor Finalisation | 2025-11-15 | 2025-11-15 | Completed |  | 5cc8579d-819d-4b78-8edf-89c8ebde1e97 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 21
22 | Plumbing: Work Order / PO Release | 2025-11-26 | 2025-11-29 | Completed |  | 61c9ccff-56ab-42dd-b685-fbc424ff2f31 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 22
23 | PACKAGE • Kitchens |  |  |  |  | 8cf786fb-938b-49f3-8b91-e196668c1585 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 23
24 | Kitchens: Vendor Evaluation (shortlist) | 2025-08-25 | 2025-08-25 | Completed |  | ed43e322-68a3-44ca-b067-f3f370ed9db7 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 24
25 | Kitchens: RFQs Issued | 2025-08-25 | 2025-08-25 | Completed |  | a1dc641b-0a9b-4bbb-872a-f847f3e61227 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 25
26 | Kitchens: Vendor Finalisation | 2025-10-15 | 2025-10-15 | Completed |  | a364be2c-149a-4a9e-b95f-b2143a271d2e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 26
27 | Kitchens: Work Order / PO Release | 2025-10-30 | 2025-10-30 | Completed |  | ada97ff3-7791-48c2-af2f-3bb338e2b2d4 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 27
28 | PACKAGE • Sanitary Fittings |  |  |  |  | 23c9bff2-c36e-454f-9453-5e8399ceda42 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 28
29 | Bathrooms: Vendor Evaluation (shortlist) | 2025-10-13 | 2025-10-13 | Completed |  | ffd20114-70ef-453a-81d9-f95ac216ee50 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 29
30 | Bathrooms: RFQs Issued | 2025-10-15 | 2025-10-15 | Completed |  | 2bcfe316-31ff-4c74-83c0-be399a579840 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 30
31 | Bathrooms: Vendor Finalisation | 2025-11-11 | 2025-11-11 | Completed |  | a284e349-8f73-4fb8-bb6a-cf0d3a907c62 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 31
32 | Bathrooms: Work Order / PO Release | 2025-11-11 | 2025-11-11 | Completed |  | fefc0bd7-3618-4e71-9c47-a7c55ecbba9c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 32
33 | PACKAGE • Audio |  |  |  |  | 6d0d904d-eca5-4b14-a2be-8b68ac131507 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 33
34 | Audio: Vendor Evaluation (shortlist) | 2025-08-12 | 2025-08-12 | Completed |  | 6174c3f9-3392-47e8-a092-29c12f25b414 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 34
35 | Audio: RFQs Issued | 2025-08-09 | 2025-08-09 | Completed |  | 8cddbd3c-0eab-490d-84ce-e6ebf2c191e1 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 35
36 | Audio: Vendor Finalisation | 2025-08-09 | 2025-08-09 | Completed |  | 5611353f-dee8-4df4-bf2c-7e777d00b3c8 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 36
37 | Audio: Work Order / PO Release | 2025-08-21 | 2025-08-21 | Completed |  | af28f5fc-5ba7-4194-bc8b-e2a296b1521d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 37
38 | PACKAGE • Automation |  |  |  |  | 1f29f9a6-3136-4ad7-b57f-a9d93c423028 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 38
39 | Automation: Vendor Evaluation (shortlist) | 2025-10-11 | 2025-10-11 | Completed |  | 2e3ef81d-faa1-4147-82a6-5c4bf804a601 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 39
40 | Automation: RFQs Issued | 2025-10-11 | 2025-10-11 | Completed |  | a21e6068-6e00-43ba-a6d1-373c9b20dd49 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 40
41 | Automation: Vendor Finalisation | 2025-10-17 | 2025-10-17 | Completed |  | 1bd83259-a96f-407b-a8c8-c3c4fae3d240 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 41
42 | Automation: Work Order / PO Release | 2025-11-17 | 2025-11-17 | Completed |  | c29d7f3e-cdbd-4c0b-90f8-05221ea82edd | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 42
43 | PACKAGE • Lighting |  |  |  |  | 0a80f47f-6fd2-4dfc-90a2-1ae7a9c6c96b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 43
44 | Lighting: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | Completed |  | 263e551e-ef11-4c62-a87a-975215fc3c8b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 44
45 | Lighting: RFQs Issued | 2025-10-09 | 2025-10-09 | Completed |  | 17ba4f81-e015-42f4-9e6a-a14c1b63df90 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 45
46 | Lighting: Vendor Finalisation | 2025-10-10 | 2025-10-10 | Completed |  | 80a11c21-bd8e-4105-9b9b-3513eb65695b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 46
47 | Lighting: Work Order / PO Release | 2025-11-17 | 2025-11-17 | Completed |  | a450fc38-dd66-4d51-a75c-3e3b917ae1c0 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 47
48 | PACKAGE • HVAC |  |  |  |  | 05fad4d3-ea79-44b6-b249-752aef22b92c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 48
49 | HVAC: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | Completed |  | 78597b12-035c-4118-b38b-ec201f09e204 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 49
50 | HVAC: RFQs Issued | 2025-10-09 | 2025-10-09 | Completed |  | c20265a5-d6c5-463e-91d6-15f96f055aeb | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 50
51 | HVAC: Vendor Finalisation | 2025-10-10 | 2025-10-10 | Completed |  | 2eedd11c-c6e1-4d06-be0f-11e2867c8d12 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 51
52 | HVAC: Work Order / PO Release | 2025-11-17 | 2025-11-22 | Completed |  | 7623241f-eb71-4dac-b477-f91b84a80362 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 52
53 | PACKAGE • Windows |  |  |  |  | 50fda314-e8a1-4a40-ad8b-5b2ea0c3a1d9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 53
54 | Doors & Windows: Vendor Evaluation (shortlist) | 2025-08-26 | 2025-08-26 | Completed |  | 116384fe-d790-4cf1-8a6c-99f170a70961 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 54
55 | Doors & Windows: RFQs Issued | 2025-08-28 | 2025-08-28 | Incomplete |  | 370c1589-2386-49c2-9e55-2b10ed331ad2 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 55
56 | Doors & Windows: Vendor Finalisation | 2025-10-24 | 2025-10-24 | Incomplete |  | 9e4c2d8b-5871-4891-b771-00d3d6c89e3b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 56
57 | Doors & Windows: Work Order / PO Release | 2025-11-17 | 2025-11-17 | Incomplete |  | 5911eb14-c752-4ce7-9d57-69bea129698b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 57
58 | PACKAGE • Wall Finishes |  |  |  |  | bd6e71b6-8b0b-4e81-9842-c848e19d86b9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 58
59 | Wall Finishes: Vendor Evaluation (shortlist) | 2025-08-08 | 2025-08-08 | Completed |  | 585f753d-415a-469c-9be9-3374d3f75c61 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 59
60 | Wall Finishes: RFQs Issued | 2025-12-05 | 2025-12-05 | Completed |  | 0beba980-be48-47b3-8acb-9aed8991aa53 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 60
61 | Wall Finishes: Vendor Finalisation | 2026-01-15 | 2026-01-15 | Completed |  | 7899dd8b-06d3-4ae0-b7ae-e7aaba00e781 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 61
62 | Wall Finishes: Work Order / PO Release | 2026-01-30 | 2026-01-30 | Incomplete |  | 90559218-62ed-4160-a02f-a0ae1cb2df33 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 62
63 | PACKAGE - FURNITURE |  |  |  |  | 0a2eb266-d58b-47d9-b663-d339a4f6e9aa | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 63
64 | Furnishing: Vendor Evaluation (shortlist) | 2026-01-10 | 2026-01-10 | Incomplete |  | 80cfd7a8-4b71-433e-9ce6-bf6fd3299c5b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 64
65 | Furnishing: RFQs Issued | 2026-01-15 | 2026-01-15 | Incomplete |  | 5078a175-37ff-478b-bfc3-58cb5859ed54 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 65
66 | Furnishing: Vendor Finalisation | 2026-02-06 | 2026-02-06 | Incomplete |  | 43184731-b225-4360-a3b6-f8e3776cb6b4 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 66
67 | Furnishing: Work Order / PO Release | 2026-02-13 | 2026-02-13 | Incomplete |  | 4d9f418e-f655-4eea-9b8e-ea08a86992c6 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 67
68 | PACKAGE • Soft Furnishing |  |  |  |  | df9278d4-6622-4474-83f7-eb9eb94b7782 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 68
69 | Soft Furnishing: Vendor Evaluation (shortlist) | 2026-02-22 | 2026-02-22 | Incomplete |  | aebac38b-b218-4498-86be-5b8fd680557a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 69
70 | Soft Furnishing: RFQs Issued | 2026-02-26 | 2026-02-26 | Incomplete |  | bb8c9297-324e-4a30-808f-a4fa8de2b4da | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 70
71 | Soft Furnishing: Vendor Finalisation | 2026-03-06 | 2026-03-06 | Incomplete |  | 0b76debd-7d2d-4f03-859c-6412f2783bc5 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 71
72 | Soft Furnishing: Work Order / PO Release | 2026-03-12 | 2026-03-12 | Incomplete |  | d782f0d3-2d2f-43db-bd5c-a4037ff0c649 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 72
73 | PACKAGE • Appliances |  |  |  |  | c671458a-ea0d-4be2-a4ae-4b4ce90d0a44 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 73
74 | Appliances: Vendor Evaluation (shortlist) | 2025-11-13 | 2025-11-13 | Incomplete |  | 25843b10-ae7e-489f-a466-b8645ba62b1d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 74
75 | Appliances: RFQs Issued | 2025-11-18 | 2025-11-18 | Incomplete |  | 1439c444-07b7-4809-bf9a-99bf70389911 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 75
76 | Appliances: Vendor Finalisation | 2025-12-10 | 2025-12-10 | Incomplete |  | 8308f210-afdf-4c2f-b092-70f7e7b50b44 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 76
77 | Appliances: Work Order / PO Release | 2025-12-15 | 2025-12-15 | Incomplete |  | 0551633c-cacc-44fa-906f-f1b8f2e0ee32 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 77
78 | PACKAGE • Flooring |  |  |  |  | d8aaebad-6509-40a2-82d1-18e24865b053 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 78
79 | Flooring: Vendor Evaluation (shortlist) | 2025-08-16 | 2025-08-16 | Completed |  | 7aa63dbe-cd1b-4bdf-8c52-bc9c6c06a17b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 79
80 | Flooring: RFQs Issued | 2025-08-16 | 2025-08-16 | Completed |  | 40926ce3-fdbc-4be9-9785-1f1ed8056e6c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 80
81 | Flooring: Vendor Finalisation | 2025-11-15 | 2025-11-15 | Completed |  | 5f83435a-0c30-4eab-9722-1b4499b55a72 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 81
82 | Flooring: Work Order / PO Release | 2025-11-17 | 2025-11-17 | Completed |  | 02f73038-ca75-44bf-8b90-33f12f6cc768 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 82
83 | PACKAGE • Carpentry |  |  |  |  | 815b88c0-8254-4c18-8e9b-20ddb4e09f4f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 83
84 | Carpentry: Vendor Evaluation (shortlist) | 2025-09-25 | 2025-10-05 | Incomplete |  | 246a4431-b2c4-4c32-ae34-813196f06469 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 84
85 | Carpentry: RFQs Issued | 2025-11-29 | 2025-11-29 | Incomplete |  | fbedb56d-c083-45b4-bf82-2f9ea45d08b9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 85
86 | Carpentry: Vendor Finalisation | 2025-11-30 | 2025-12-04 | Incomplete |  | a97e1b6a-3d2e-41f9-981b-21c48d1e179a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 86
87 | Carpentry: Work Order / PO Release | 2025-12-05 | 2025-12-05 | Incomplete |  | e54131b7-2a65-46b8-aefe-cecd45170464 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 87
88 | PHASE • Execution (Category-wise) |  |  |  |  | 207727f7-03fb-400e-9c3f-7e0cafea4478 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 88
89 | EXECUTE • Civil |  |  |  |  | f4f68fb5-eef1-4b9e-b462-e402ed0f8631 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 89
90 | Civil: Drawings plans & elevations | 2025-03-20 | 2025-03-24 | Incomplete |  | 39afd1e5-50c7-42af-84d9-d836b981c27b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 90
91 | Civil: Drawings checking | 2025-03-25 | 2025-09-15 | Completed |  | 649c01d3-6230-404c-a682-f6159350fc7b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 91
92 | Civil: Drawings Revisions | 2025-09-16 | 2025-09-20 | Completed |  | 5602cd23-337f-48c2-a5e0-2b3f629e199d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 92
93 | Civil: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | 0864fd8f-f3b1-4b78-8e92-2a628b1d7815 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 93
94 | MaterialDelivery on site | 2025-07-02 | 2025-07-07 | Completed |  | e4793038-7002-4fbb-bf48-a74c71ef8a44 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 7.00 | 94
95 | Civil: Installation / Execution | 2025-07-02 | 2025-12-10 | Incomplete |  | 6e765417-1eb9-4e18-bae7-d845212defad | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 95
96 | Civil: Testing & Commissioning / QA‑QC | 2026-12-11 | 2026-12-13 | Incomplete |  | bac5e75b-488d-4f1b-b144-8b367bc7d051 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 96
97 | EXECUTE • Plumbing |  |  |  |  | b274b533-efaa-4f77-ba58-36b7bd86e517 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 97
98 | Music Room: Drawings plans & elevations | 2025-11-25 | 2025-12-05 | Incomplete |  | 2828957c-d319-421d-b719-04691c3e264f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 98
99 | Master Bedroom: Drawings Plans & Elevations | 2025-11-28 | 2025-12-05 | Incomplete |  | 78caf6f4-8462-4c43-bac7-f4368991c8f9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 99
100 | Chitra's Room: Drawings Plans & elevations | 2025-11-30 | 2025-12-05 | Incomplete |  | e314a5ae-add5-47f3-8d0f-0b19d389f883 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 100
101 | Powder Room: Drawings Plans & Elevations | 2025-11-30 | 2025-12-05 | Incomplete |  | e608ec22-95e0-45df-be11-3d9e1368ee5c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 101
102 | All Bathrooms: Drawings checking | 2025-12-02 | 2025-12-06 | Incomplete |  | 87681041-5a46-49a1-b7da-445576577928 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 102
103 | All Bathrooms: Revisions | 2025-12-05 | 2025-12-08 | Incomplete |  | 8453b079-2bc7-4faf-b6c6-4121d16f0028 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 103
104 | Plumbing: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | cf3eabbb-3c7d-471f-8c79-2c68d91a9830 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 104
105 | Plumbing: Material delivery to site | 2025-12-09 | 2025-12-13 | Incomplete |  | 3b0178c6-f53a-43b5-bf67-cd2912c6a169 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 105
106 | Plumbing: Execution | 2025-12-09 | 2025-01-05 | Incomplete |  | bcad5774-f43b-4d32-b96c-da4e43bc8233 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 106
107 | Plumbing: Installation | 2026-05-08 | 2026-05-17 | Incomplete |  | 116b9ca2-e497-4c70-a12a-cae1697fc47a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 107
108 | Plumbing: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | Incomplete |  | 7df94596-cea8-44e8-b9e1-6e79890b9599 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 108
109 | EXECUTE • Kitchens |  |  |  |  | 4408c129-be5c-495a-a777-0fde4eab90f2 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 109
110 | Kitchen: Drawings Plans & elevations | 2026-01-15 | 2026-01-30 | Incomplete |  | ac0e37e3-d1f5-4780-b98a-e3bc4fc05746 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 110
111 | Kitchen: Drawings checking | 2026-01-30 | 2026-02-02 | Incomplete |  | ffaca922-5c7f-47fb-91ce-52ed8e0838ac | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 111
112 | Kitchen: Drawings Revisions | 2026-02-03 | 2026-02-05 | Incomplete |  | b27306aa-ed2f-4c01-a643-3e22b62234c4 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 112
113 | Kitchens: Fabrication / Off‑site Prep (if applicable) | 2026-02-06 | 2026-06-07 | Incomplete |  | 444de8a0-1b15-4fe2-8b76-4155d2838554 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 113
114 | Kitchens: Material delivery to site | 2026-06-10 | 2026-06-15 | Incomplete |  | 4b37487c-488f-4ec6-9770-a4ad59181b24 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 114
115 | Kitchens: Installation / Execution | 2026-06-15 | 2026-07-20 | Incomplete |  | da1c5fd0-f901-49b9-b2dd-bec7ce0319e5 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 115
116 | Kitchens: Testing & Commissioning / QA‑QC | 2026-07-21 | 2026-07-28 | Incomplete |  | 3a4fc742-3649-45e7-9961-36a832b71fac | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 116
117 | EXECUTE • Bathrooms |  |  |  |  | ec661580-0887-4025-877c-96ac6eb9b2b5 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 117
118 | Music Room: Drawings plans & elevations | 2025-11-25 | 2025-12-05 | Incomplete |  | c18ee329-27f3-44c1-b4df-b6805fd5f904 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 118
119 | Master Bedroom: Drawings Plans & Elevations | 2025-11-28 | 2025-12-05 | Incomplete |  | 6869ebfe-1f2c-4cfc-a70a-89e3d9f553ea | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 119
120 | Chitra's Room: Drawings Plans & elevations | 2025-11-30 | 2025-12-05 | Incomplete |  | 682c8ddd-e385-49aa-a212-4f68e6a0f571 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 120
121 | Powder Room: Drawings Plans & Elevations | 2025-11-30 | 2025-12-05 | Incomplete |  | 42325ae9-2501-4275-825a-22064f022d8f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 121
122 | All Bathrooms: Drawings checking | 2025-12-05 | 2025-12-08 | Incomplete |  | b2ec1c6a-8b36-44e9-99a4-7493b5d42089 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 122
123 | All Bathrooms: Revisions | 2025-12-09 | 2025-12-12 | Incomplete |  | 1bd18a65-3357-4568-9c63-013b530dd3c9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 123
124 | Bathrooms: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | 08968c02-3d83-4988-af17-d827021cea4d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 124
125 | Bathrooms: Finishing Material delivery to site | 2025-12-08 | 2025-12-13 | Incomplete |  | f5d4989d-33f5-4414-b4a8-1115cdf5e609 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 125
126 | Bathrooms: Execution | 2026-01-06 | 2026-02-06 | Incomplete |  | 9dd81206-9855-4926-b788-081ee3fe087e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 126
127 | Bathrooms: Installation | 2026-05-08 | 2026-05-17 | Incomplete |  | e7e0e27d-4b12-4876-9bc5-4df22e8afaf8 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 127
128 | Bathrooms: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | Incomplete |  | ded87e31-b5d4-464e-82c3-dbd5d18d8aa3 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 128
129 | EXECUTE • Audio |  |  |  |  | db275ce4-cfb5-4c6d-bf72-c72c35f74d38 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 129
130 | Audio: shop Drawings | 2025-12-03 | 2025-12-05 | Incomplete |  | 52ec2c3f-9453-4abe-aaa5-6cd441d48862 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 130
131 | Audio: Drawings checking | 2025-12-06 | 2025-12-10 | Incomplete |  | 14e4af40-3690-4feb-b284-f5c84f0ba1bf | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 131
132 | Audio: Revisions | 2025-12-11 | 2025-12-13 | Incomplete |  | e133e55e-dc79-4fe7-809a-4b1c01abcc67 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 132
133 | Audio: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | 27547190-ebe1-461d-8b7f-8b34103f9529 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 133
134 | Audio: Material delivery to Site- Speakers, wires & Cables | 2025-12-25 | 2025-12-29
135 | Audio: Material delivery to Site - Speakers , Music system | 2026-07-10 | 2026-07-15 | Incomplete |  | f87f3688-b03c-432e-b55b-d69e76db55ee | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 134
136 | Audio: Execution | 2025-12-25 | 2026-01-25 | Incomplete |  | 1a0946f7-7168-4624-a463-35b7784b0240 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 135
137 | Audio: Installation | 2026-07-15 | 2026-07-22 | Incomplete |  | 23857c45-5782-4a00-aa5b-574711fff88d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 136
138 | Audio: Testing & Commissioning / QA‑QC | 2026-07-23 | 2026-08-01 | Incomplete |  | b86f03b6-6986-4091-987d-8eefae1ba049 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 137
139 | EXECUTE • Automation + Electricals + lighting |  |  |  |  | 53029187-01ac-4a44-b1be-3dec4a00201b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 138
140 | AEL: shop drawings | 2025-11-27 | 2025-12-02 | Incomplete |  | 1416648d-56f9-4032-84d5-634d16d1fb6e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 139
141 | AEL: Drawings checking | 2025-12-03 | 2025-12-05 | Incomplete |  | 54f8803d-b2ab-478b-af3e-57a33c697216 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 140
142 | AEL: Revisions | 2025-12-05 | 2025-12-08 | Incomplete |  | 6ea4f61d-25b1-4262-a0f8-cf70cd6d9a28 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 141
143 | AEL: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | 1c474f67-22e4-41a2-af67-276bcd58cb20 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 142
144 | Automation: Material delivery to site | 2026-01-27 | 2026-01-01 | Incomplete |  | 9149fae6-4d1b-4a96-9878-b994841d282e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 143
145 | AEL: Execution | 2025-12-02 | 2026-01-02 | Incomplete |  | 2daae59b-7ef3-450e-bb12-571cbec7e058 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 144
146 | AEL: Installation | 2026-05-08 | 2026-05-17 | Incomplete |  | 83455657-439b-406a-962c-6962afd0eb72 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 145
147 | AEL: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | Incomplete |  | ef0c1d49-39ef-47f4-822a-ef015319df08 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 146
148 | EXECUTE • HVAC |  |  |  |  | 8e79a7f0-b59b-47ed-8c14-56dcfff66e19 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 147
149 | HVAC: shop drawings | 2025-11-09 | 2025-11-11 | Completed |  | 5116266c-df1f-4f68-af22-f0504b9464ab | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 148
150 | HVAC: Drawings checking | 2025-11-11 | 2025-11-11 | Completed |  | 02fb6958-5b77-4ab5-a2b8-cc63de307659 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 149
151 | HVAC: Revisions | 2025-11-11 | 2025-11-11 | Completed |  | aec8715d-0363-45fe-8731-0779b2c29492 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 150
152 | HVAC: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | ba56328a-f5d3-446c-8c77-eeb027f7cbbd | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 151
153 | HVAC:Material delivery to site | 2026-05-06 | 2026-05-08 | Incomplete |  | 6637205c-c7e9-490e-8b7b-3c3fb070130c | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 152
154 | HVAC: Execution | 2025-12-02 | 2026-01-02 | Incomplete |  | 34a0f0fd-a048-48b6-b1c6-6f07568f3bc7 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 153
155 | HVAC: Installation | 2026-05-08 | 2026-05-17 | Incomplete |  | 8cb616a1-1283-4386-b198-afbda0c5960a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 154
156 | HVAC: Testing & Commissioning / QA‑QC | 2026-05-18 | 2026-05-25 | Incomplete |  | 3ca46f9b-2d81-4b53-af10-45af8848d245 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 155
157 | EXECUTE • Windows |  |  |  |  | 224512ad-f31c-472f-b948-8871c159c1d2 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 156
158 | Windows: shop drawings | 2026-01-10 | 2026-01-17 | Incomplete |  | c4257457-8835-44f4-98e4-ef545728aad5 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 157
159 | Windows: Drawings checking | 2026-01-19 | 2026-01-22 | Incomplete |  | 2cd03ac2-c22e-4bbb-b0dc-25d54d9dac13 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 158
160 | Windows: Revisions | 2026-01-23 | 2026-01-25 | Incomplete |  | 77d243d7-220b-494f-82d8-3799dc7cc521 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 159
161 | Windows: Fabrication / Off‑site Prep (if applicable) | 2026-01-25 | 2026-06-10 | Incomplete |  | cfb60aab-a5c0-4e08-af5f-7fe6f69f2321 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 160
162 | Windows: Material delivery on site | 2026-06-15 | 2026-06-25 | Incomplete |  | 93254b34-d83c-44a7-b75a-43974e7906f0 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 161
163 | Windows: Installation / Execution | 2026-06-25 | 2026-07-05 | Incomplete |  | fd02448c-4171-49d6-8b61-b04c72953e57 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 162
164 | Windows: Testing & Commissioning / QA‑QC | 2026-07-06 | 2026-07-10 | Incomplete |  | c0654913-22ef-419e-b68b-25d38b4ee57a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 163
165 | EXECUTE • Wall Finishes |  |  |  |  | 939a01f6-29ec-4c33-815b-cb3dc23a183d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 164
166 | Wall Finishes: Material delivery on site- plaster of paris | 2025-12-05 | 2025-12-06 | Incomplete |  | aa6f4720-516f-4267-8d1c-4240df25be88 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 165
167 | Wall Finishes: Fabrication / Off‑site Prep (if applicable) |  |  | Incomplete |  | 97bf8831-0234-493b-8fa6-2d6ff843baec | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 166
168 | Wall Finishes: Material delivery on site- Wall paper | 2026-07-15 | 2026-07-20 | Incomplete |  | bc0260bf-fe32-460f-9189-eb5f1fc7abfa | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 167
169 | Wall Finishes: Execution - Plaster of Paris works | 2025-12-07 | 2026-02-10 | Incomplete |  | b9f834fd-b46e-49ce-bc04-e65916c9abe7 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 168
170 | Wall Finishes: Installation / Execution - Wall paper/paint/limewash | 2026-03-01 | 2026-07-31 | Incomplete |  | 41d5e21b-0675-4b5d-bb30-7c71bd56433b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 169
171 | Wall Finishes: Testing & Commissioning / QA‑QC | 2026-08-01 | 2026-08-05 | Incomplete |  | 130a1699-e4bb-467e-8502-4cda6d45b563 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 170
172 | EXECUTE • Furnishing |  |  |  |  | 79141ab1-e128-40ce-b365-9c30b91b75e7 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 171
173 | Furnishing: Fabrication / Off‑site Prep (if applicable) | 2026-02-13 | 2026-06-25 | Incomplete |  | fd436422-29a6-4078-9c06-638365b73948 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 172
174 | Furnishing: Material delivery on site | 2026-02-26 | 2026-07-15 | Incomplete |  | ac8b6b21-0e65-4eb9-b789-18aeac5dc392 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 173
175 | Furnishing: Installation / Execution | 2026-07-15 | 2026-07-31 | Incomplete |  | 6d764e95-5be7-4468-9ca6-65a5a30e8e64 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 174
176 | Furnishing: Testing & Commissioning / QA‑QC | 2026-08-01 | 2026-08-05 | Incomplete |  | cb3d393b-1d45-40ec-9d9c-7eb2ec4ab4b9 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 175
177 | EXECUTE • Soft Furnishing |  |  |  |  | 06d3004e-bd01-402c-a883-4d03b59e3036 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 176
178 | Soft Furnishing: Fabrication / Off‑site Prep (if applicable) | 2026-03-15 | 2026-07-20 | Incomplete |  | 8d732f73-7a14-4e37-8581-89109d915707 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 177
179 | Soft Furnishing: Material delivery on site | 2026-07-21 | 2026-07-31 | Incomplete |  | a72ac55c-f3e5-4f56-b829-87c39c05b273 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 178
180 | Soft Furnishing: Installation / Execution | 2026-07-20 | 2026-08-01 | Incomplete |  | 0508f670-38a3-4736-bfd4-14e0aa36831e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 179
181 | Soft Furnishing: Testing & Commissioning / QA‑QC | 2026-08-02 | 2026-08-07 | Incomplete |  | ffbb9683-59c9-4333-8b2c-c9f7530541b1 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 180
182 | EXECUTE • Appliances |  |  |  |  | 6ba683ff-04f3-46ea-bdcf-c862c8645c38 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 181
183 | Appliances: Fabrication / Off‑site Prep (if applicable) | 2025-11-19 | 2025-12-01 | Incomplete |  | cf53b67d-4741-4e39-8446-cb9cee043da6 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 182
184 | Appliances: Material delivery on site | 2026-08-01 | 2026-08-05 | Incomplete |  | c008f93f-5346-4138-a6c5-dd20c8404cf1 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 183
185 | Appliances: Installation / Execution | 2026-08-17 | 2026-08-22 | Incomplete |  | 525b0746-7984-4227-a3a9-f13e06235864 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 184
186 | Appliances: Testing & Commissioning / QA‑QC | 2026-08-23 | 25 Ayg 2026 | Incomplete |  | 7c3aaf16-bf7f-48a9-961d-c4727c8bdcff | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 185
187 | EXECUTE • Flooring |  |  |  |  | 7c54097f-4565-476d-a0c9-b307117abe92 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 186
188 | Flooring: drawings plan | 2025-12-04 | 2025-12-08 | Incomplete |  | 2b88f473-3a34-4b2e-be46-284655e33938 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 187
189 | Flooring: Drawings checking | 2025-12-09 | 2025-12-11 | Incomplete |  | 73dc1573-3327-4c49-a7bd-c8d39f519f5a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 188
190 | Flooring: Revisions | 2025-12-12 | 2025-12-12 | Incomplete |  | e6d179de-a826-4527-afdb-96ef1d1f8245 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 189
191 | Flooring: Fabrication / Off‑site Prep (if applicable) | 2026-01-05 | 2026-07-01 | Incomplete |  | 200aec82-c2bc-49dd-8ae7-c0ff1bc84185 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 190
192 | Flooring: Material delivery on site | 2026-07-06 | 2026-07-16 | Incomplete |  | 682e2a19-3895-42d8-be92-ef0b8f723d29 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 191
193 | Flooring: Installation / Execution | 2026-07-16 | 2026-08-01 | Incomplete |  | bc426347-82ea-4a77-94eb-e6084f32a1bd | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 192
194 | Flooring: Testing & Commissioning / QA‑QC | 2026-08-02 | 2026-08-08 | Incomplete |  | 32e10a89-2ef7-4ece-8053-33c943f415ff | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 193
195 | EXECUTE • Carpentry |  |  |  |  | 5304143b-dac6-40df-958f-5ebe7c403694 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 194
196 | Carpentry: shop drawings fixed furniture sketches | 2025-11-05 | 2025-12-05 | Incomplete |  | 317e9cb2-36f9-449a-8b4a-108ba4c3e276 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 195
197 | Carpentry: shop drawings fixed furniture: checking | 2025-11-17 | 2025-12-06 | Incomplete |  | 5c8707e0-24a4-4ec2-9f15-8383b7981d97 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 196
198 | Carpentry: shop drawings fixed furniture: revisions | 2025-11-20 | 2025-12-08 | Incomplete |  | 3787a2a7-e0dd-46db-94ae-bfef8d58fc4f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 197
199 | Carpentry: Material delivery at workshop | 2025-12-08 | 2025-12-11 | Incomplete |  | 17f20aa6-2032-42e1-b302-27489486708a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 198
200 | Carpentry: Fabrication / Off‑site Prep (if applicable) | 2025-12-11 | 2026-03-20 | Incomplete |  | 192a6391-9411-427e-84a1-1b931002fa4d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 7.00 | 199
201 | Carpentry: Installation / Execution | 2026-03-23 | 2026-05-23 | Incomplete |  | be93c10b-c2b0-4d69-9d2c-23cb16aa98ae | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 200
202 | Carpentry: Testing & Commissioning / QA‑QC | 2026-05-24 | 2026-06-05 | Incomplete |  | 319d151e-9a11-4ff2-b4ba-2eaf693c3d1d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 2.00 | 201
203 | LINK • Flooring waits for Civil |  |  | Incomplete |  | 2b70ef9c-0191-4433-97df-38044779faaa | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 202
204 | LINK • Wall Finishes wait for Civil |  |  | Incomplete |  | 37578472-f4bd-4b82-95a1-371f4384e3dc | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 203
205 | LINK • Doors & Windows wait for Civil |  |  | Incomplete |  | bc1bd6fc-b8ca-43e3-8c37-7fc39d40e01b | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 204
206 | LINK • Carpentry waits for Civil |  |  | Incomplete |  | cfb542c5-b7be-4b8a-a1cd-6ed596f4d145 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 205
207 | LINK • Lighting after Electricals |  |  | Incomplete |  | c6827ec8-99fb-4997-b8eb-447bcee47b81 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 206
208 | LINK • Automation after Electricals |  |  | Incomplete |  | b1988bdc-65e1-4ee8-99b5-1f9f6e24af56 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 207
209 | LINK • Audio after Electricals |  |  | Incomplete |  | 9929fd3d-13cc-4fa3-b4bb-a6a2b42c2ea8 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 208
210 | LINK • Kitchens after Plumbing |  |  | Incomplete |  | 765da3a9-78e2-4911-959b-cf8f4a27342a | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 209
211 | LINK • Bathrooms after Plumbing |  |  | Incomplete |  | 0efff8b5-acbc-4b48-94c2-fa5c7decd2dc | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 210
212 | LINK • Appliances after Kitchens & Electricals |  |  | Incomplete |  | 726a7aa6-67c2-47c6-93b5-ae2c46313c34 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 211
213 | PHASE • Closeout & Handover |  |  |  |  | 93ad5d01-db41-44a1-8f0b-56b2f01da6ba | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM |  | 212
214 | All Trades Complete – Declaration | 2026-08-09 | 2026-08-11 | Incomplete |  | 0872849e-853d-4913-84a6-1945a749b68e | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 0.00 | 213
215 | Snagging / Punch List | 2026-08-12 | 2026-08-21 | Incomplete |  | 6595b73d-32aa-44e2-956d-cab7532ee582 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 3.00 | 214
216 | Rectification of Snags | 2026-08-16 | 2026-08-25 | Incomplete |  | 390d14f4-726e-4e7e-a00f-0dd9d9c2bd3f | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 215
217 | Client Demo & Acceptance | 2026-08-27 | 2026-08-29 | Incomplete |  | 7e729385-e1c4-42cc-8e8f-ac726f5a90d6 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 216
218 | Practical Completion / Handover | 2026-09-01 | 2026-09-01 | Incomplete |  | 9c55d28c-1d3f-43bc-9007-17e7342c1b8d | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 1.00 | 217
219 | As‑Built Docs & O&M Manuals | 2026-09-02 | 2026-09-05 | Incomplete |  | b33c5b48-7bfd-46f4-a5a4-54e5e677bf00 | 748f963d-aa53-44ad-9678-8b243a06531b | MEDIUM | 5.00 | 218
SUMMARY
Total Tasks: 219
Completed: 51(23%)
Incomplete: 168

## Instructions
Topic | Description
Purpose | This is your Designer Export file. Edit dates here, then re-import to sync changes back to the system.
DATE FORMAT | Enter dates in any of these formats:
• 15 Nov 2025 (recommended)
• 2025-11-15
• 15/11/2025
• Nov 15, 2025
STATUS | The Status column has a dropdown toggle:
• Click the dropdown arrow in any Status cell to toggle between options
• "Incomplete" - Task is not yet done (default)
• "Completed" - Task is finished
• You can also type directly: "Incomplete" or "Completed"
SECTION HEADERS | Rows containing PHASE, PACKAGE, or EXECUTE are section headers.
Leave dates and status blank for these rows.
RE-IMPORT | After editing, use the "Re-import" button in the app to sync your changes.
The system will update dates, progress, and remarks for each task.
HIDDEN COLUMNS | Columns G onwards contain system IDs. Do NOT modify or delete these.
They are used to match tasks during re-import.